Hospital
 Data Analysis Project

Data Analyst: Bushra Fawaz Alsubhi

Client/Sponsor: Hospital Administration

Purpose:

The importance of this project lies in analyzing hospital data to understand patient flow, waiting times, and department performance, and to suggest solutions to improve workflow and patient satisfaction. The goal is to identify areas for improvement to reduce waiting time and monitor service quality.

The project focuses on analyzing patient waiting times and evaluating department performance to identify potential areas for improvement.

Scope / Major Project Activities:

What are the major parts of this project? List out the high-level steps, activities, or stages of the project, and give a brief description for each.

| Activity | Description |
| --- | --- |
| Data Preparation | Prepare a synthetic hospital dataset containing patient visits, appointments, departments, arrival times, and provider service times. |
| Data Cleaning | Review and clean the data by identifying missing values, duplicates, inconsistencies, and data-entry errors. |
| Data Analysis | Analyze patient volume, waiting times, appointment patterns, and department performance. |
| Data Visualization | Create charts or a dashboard to clearly communicate trends, patterns, and key performance indicators. |
| Reporting | Summarize key findings, conclusions, and recommendations based on the analysis. |

This project does not include:

- This project does not include providing medical treatment or making clinical decisions.

- It does not include financial or insurance analysis

- It does not include predictive modeling or machine learning

- It does not include modifying hospital systems

- It does not include data outside the hospital

Deliverables:

A specific list of things that your project will deliver.

| Deliverable | Description/ Details |
| --- | --- |
| Excel Data Analysis Workbook | Structured workbook containing data preparation, data cleaning, analysis questions, analysis results, insights, conclusions, and recommendations. |
| Visualizations / Dashboard: | Charts or a dashboard presenting key findings about patient volume, waiting times, and department performance. |
| Recommendations | Suggested actions based on the analysis to reduce waiting time and improve service quality. |

Schedule Overview / Major Milestones:

The expected schedule for the project. This can be defined by milestones (e.g. “all data is cleaned and processed”), periods of time (“Week 1 / Week 2”), or other ways based on the needs of the project.

| Milestone | Expected Completion Date | Description/Details |
| --- | --- | --- |
| Data Preparation | 3 day | Create and prepare the synthetic hospital dataset |
| Data Cleaning | 5 day | Clean and prepare the data for analysis |
| Data Analysis | 9 day | Analyze waiting times and department performance |
| Data Visualization | 10 day | Create a dashboard to visualize results |
| Final Review & Recommendations: | 11 day | Prepare final report and recommendations |

*Estimated date for completion:

This is my “if all goes well and I have everything I need, this is when I’ll be done” date.

Estimated completion date: 11 days from the project start date if all phases go as planned, with an additional 5-day buffer in case of delays